## Slide 1: SIT374: Project Management
Lecture 2: Project Initiating

## Slide 2: Project process management groups - Initiation
Initiation
Planning
Executing
Closing
Monitoring
Control
Approved Project Charter
Approved Project Management Plan
Customer signoff
Completion Report

## Slide 3: Management process – Activity Map
Initiation
Planning
Executing
Mon. & Con.
Closing
Project Charter
Stakeholders
Register
Project Plan
Scope
Time
Cost
Quality
HR
Risk
Procurement
Stakeholders
Comm.
Project
Closing
Contract
Closing
Acquire & manage
team
Select Sellers &
POs
Perform QA
Comm.
Monitor &
Control Proj.
Scope control &
verification
Schedule/
Cost/risk control
Progress Reporting
Manage Stakeholders
Contract Admin


## Slide 4: PROJECT Initiation
To officially initiate a project, the main tasks are to identify all stakeholders and develop the project charter.

## Slide 5: PROJECT CHARTER
Project charter: a document that formally recognizes the existence of a project and provides direction on the project’s objectives and management.
  It authorizes project manager to use organization’s resources to complete the project.
  A Project Charter is created at the beginning of a project, approved by the stakeholders, and signed off before work can begin.

## Slide 6: 1. Develop Project Charter

## Slide 7: Business case
A document that most commonly used to create project charter
  It could be created from market demand, organizational need, customer request, etc.
  It is used to justify and create boundaries for the project.
  Financial (cost-benefit) analysis would be carried out to facilitate decision-making.
  Sample Business Cases

## Slide 8: Financial considerations
Can compare projects based on
  Net present value (NPV)
  Return on Investment (RoI)
  Payback analysis

## Slide 9: Cost vs. Revenue vs. Profit
Cost is resources expended to achieve a goal
Revenue is the income from the normal business activities
Profit (net benefit) = Revenue (benefit) – Cost (expenditure) (To increase profit : Reduce cost or Increase revenue)
Return on Investment (RoI) = (Revenue – Cost) / Cost

## Slide 10: Time-value-of-money
What is the relationship between $1 today and $1 tomorrow?
Is it worth the same 1$ today as 1$ tomorrow/yesterday?

## Slide 11: Activity 1 - An example
A project that requires an initial investment of $10,000 and will generate cash inflows of $3,000 annually for 5 years.
While the sum of the cash inflows is greater than the initial investment (net benefit is positive), can we say the project is worthy of investment?

## Slide 12: Present value (PV) and net present value (NPV)
Present Value (PV): all costs/benefits are calculated using today’s dollars
  1$ received next year may only worth 0.9$ this year
  Discount rate is introduced to account for this phenomenon
Net Present Value (NPV): all costs/benefits are calculated using today’s dollars and they are combined to get a net value
  When net benefit (without considering the discount) is positive, the net benefit (with the discount) might be negative
  The discount effect could affect decision-making in investment

## Slide 13: Discount rate and discount factor
Discount rate: the annual percentage rate/percentage rate in (project) unit time that an amount of money is discounted to bring it to a present value
  PV=(amount in the next time unit)/(1+discount rate)
Discount factor: the accumulation of discounts in the entire period based on the discount rate
  PV=(amount in the future)*1/(1+discount rate)(number of time units)
Discount factor

## Slide 14: Back to the example
A project that requires an initial investment of $10,000 and will generate cash inflows of $3,000 annually for 5 years.
What is the NPV if the discount rate for future cash flows is high (e.g., 20%)?

## Slide 15: NPV vs. discount rate

## Slide 16: NPV analysis
If… | It indicates… | Then…
NPV > 0 | the investment would add value to the firm | the project may be accepted
NPV < 0 | the investment would subtract value from the firm | the project should be rejected
NPV = 0 | the investment would neither gain nor lose value for the firm | indifferent in the decision This project adds no monetary value. Decision should be based on other criteria, e.g., strategic positioning or other factors not explicitly included in the calculation.

## Slide 17: Return on investment (Roi)
RoI: it has become trivial to calculate RoI by incorporating discounts
  RoI=(total discounted benefits-total discounted costs)/(total discounted costs
  =NPV/total discounted costs
  Can be used to compare different options
  Organizations may have a minimum acceptable ROI for projects

## Slide 18: payback
Payback period: the amount of time it will take to recoup, in the form of net benefit.
  Can be calculated based on either discounted or non-discounted analysis

## Slide 19: Activity 2
Calculate the net present value, and the return on investment using a discount rate of 8 percent for the following systems development project. The development costs for the system were $225,000

## Slide 20: Organizational structure
3 basic organization structures
  Functional: functional managers report to the CEO
  Project: program managers report to the CEO
  Matrix: middle ground between functional and project structures; personnel often report to two or more bosses; structure can be weak, balanced, or strong matrix

## Slide 21: Organizational Structures

## Slide 22: Impact of Organizational structure

## Slide 23: Organizational process assets
Standard policies, processes, and procedures
  Is there a standard process for developing and getting approval for a project charter?
Templates
  Is there a standard format for project charters?
Historical information and lessons learned
  Are there records for previous projects and documents?
  Any information on previous project performance?

## Slide 24: Project Charter – typical contents
Without the project charter, no project exists (PMPBOK)
  Project Objective
  Project Justification
  Project Constraints
  Project Risks
  Stakeholders Commitment.
  Your name
Sample Project Charter

## Slide 25: Activity 3
Look into Sample Project Charter for IT System Update
What are the issues?

## Slide 26: 2. Develop Stakeholders Register
The successful completion of a project depends on satisfying your project stakeholders.
How to identify stakeholders?
  Internal [Team, Employee, Owners]
  External [Customers, Suppliers, Investors, Governments]

## Slide 27: Activity 4
Who are the key stakeholders in Hope Health case study?

## Slide 28: STAKEHOLDER REGISTER
Stakeholder Register - a public document that includes details related to the identified project stakeholders

## Slide 29
You have been appointed as the project manager, now what? 

## Slide 30: Project process management groups - planning
Initiation
Planning
Executing
Closing
Monitoring
Control
Approved Project Charter
Approved Project Management Plan
Customer signoff
Completion Report

## Slide 31: Project Management Plan
Completion of project initiation is the signal that the project has approval to proceed to planning.
A project management plan is a document used to coordinate all project planning documents and guide project execution.
Project Management Plan required - Integration of all other plans - information is required from all other knowledge areas.

## Slide 32: Project Management Plan
Project Management Plan includes
The project name, description, sponsor’s name, description of the project, project organization
Major work packages (scope baseline): WBS, key products
Schedule information section (schedule baseline): Gantt Chart, Network Diagram (activities and dependencies)
Budget information section (cost baseline): Summary budget, Detailed budget
Subsidiary management plans: scope, schedule, cost management plans, etc.
Other sections: project life cycle description, development approach

## Slide 33: Summary
Initiation input
  Business case, organizational process assts, etc.
  Financial analysis
Initiation activities
  Develop project charter
  Develop stakeholder register
Project management plan
  Output of initiation process serves as input to planning
  Planning result in project management plan

## Slide 34: What’s next
Project planning - plan for scope, time, cost…