## Slide 1: SIT374/764: Project Management
Lecture 4: Time management (part 1)

## Slide 2: Project management process groups
Initiation
Planning
Executing
Closing
Monitoring
Control
Approved Project Charter
Approved Project Management Plan
Customer signoff
Completion Report

## Slide 3: Project management process groups-Activity Map
Initiation
Planning
Executing
Mon. & Con.
Closing
Project Charter
Stakeholders
Register
Project Plan
Scope
Time
Cost
Quality
HR
Risk
Procurement
Stakeholders
Comm.
Project
Closing
Contract
Closing
Acquire & manage
team
Select Sellers &
POs
Perform QA
Comm.
Monitor &
Control Proj.
Scope control &
verification
Schedule control
Progress Reporting
Manage Stakeholders
Contract Admin

## Slide 4: How important is “time”?
Time has the least flexibility
  Passes no matter what happens to the project
  Delivering project on time is difficult
What affects time?
  Individual characteristics
  Cultural differences
  Scope changes in project

## Slide 5: Activity 1
You are an IT project manager overseeing the development of a new project management software. The software is intended to help organizations track their projects, allocate resources efficiently, and enhance team collaboration. The project was initially estimated to take 6 months to complete, with a team of 10 developers, two designers, and three testers.
Three months into the project, you realize that the project is significantly behind schedule. Upon reviewing the project's progress, you discover several time management issues:
Frequent Overruns: You notice that development tasks consistently take longer than estimated. Despite the developers' expertise, the time allocated for each task has been underestimated.
Multitasking: Team members are often pulled between multiple tasks, causing a loss of focus and productivity. The context switching has led to delays and errors, which further consume time for corrections and rework.
Scope Creep: The project scope has gradually expanded. New features and functionalities were added without proper review or adjustment to the project timeline. This scope creep has added more work than originally planned.
Communication Gaps: There seems to be a lack of clear communication among team members, leading to confusion about task priorities and deadlines. This has resulted in some critical tasks being delayed or overlooked.

## Slide 6: Activity 1 (cont’d)
Given this situation:
a. Analyze how each identified issue contributes to the project's time management problems.
b. Propose specific strategies or practices that could be implemented to address each of these time management issues.

## Slide 7: Processes in Time Management
Define Activities
Sequence
Activities
Resourcing/Estimate Activities Durations
Develop Schedule
Control
the Schedule
Plan schedule management
Planning
Monitoring and
Controlling

## Slide 8: 1. Plan schedule management
Plan schedule management is the process of establishing policies, procedures, and documentation for planning, developing and controlling the project schedule.
Key inputs include the project charter, scope management plan, development approach, and organizational process assets.
The main output is the schedule management plan.
Sample Schedule Management Plan

## Slide 9: schedule management plan
Schedule management plan is a component of project management plan that establishes criteria/activities for developing, monitoring and controlling the schedule. Can establish the following:
  Tools/techniques used to develop schedule
  Units of measure
  Rules of performance measurement
  Reporting format

## Slide 10: 2. Define Activities
An activity (or task) is an element of work
  Normally in WBS
  Has duration, cost, and resource needs
Schedules grow out of documents that initiate a project
  Project charter – start/end dates, and budget
  Scope and WBS define what will be done
Activity list & attributes, milestone list

## Slide 11: 2. Define Activities (cont’d)
In developing task details
  Create activity list
  Activity attributes
  Milestones
Activity list includes: ID, Name and description
Activity attributes provide more information from above
  Predecessors and successors
  Leads and lags
  Resources requirements and constraints

## Slide 12: Activity list and WBS
Produce study report
Develop a survey
Analyze survey results
Perform research
Draft/edit report
Produce final report
WBS item
Activity list items

## Slide 13: Activity list and WBS
Activities are elements of work performed to complete work packages/deliverables.
  It is used to develop schedule.
Work packages is focused on outcomes rather than activities needed to produce these outcomes.
  It is used to define and organize scope
In simple scenarios, activity list exactly uses the WBS items.

## Slide 14: Lead and lag
A predecessor activity is an activity that comes before a successor (dependent) activity. A successor activity is a dependent activity that logically comes after another activity.
Lag: the amount of time a successor will be delayed with respect to its predecessor
  Represents delay
Lead: the amount of time a successor can be advanced with respect to its predecessor
  Represents acceleration
Appropriately applied lead and lag times enable more accurate and efficient scheduling.

## Slide 15: Activity 2
You are managing a project to launch a new online learning platform. The project involves several key tasks that need to be coordinated in a way that ensures the project stays on schedule. Use the concepts of lead and lag to answer the following:
Defining Lead and Lag: Explain the difference between lead and lag in the context of project scheduling.

## Slide 16: Activity 2 (cont’d)
  Task A: Development of the platform's user interface (UI) is expected to take four weeks.
  Task B: Development of the backend system cannot start until the UI design is approved, but backend developers could have two weeks before UI development completion to set up their development environment.
  Task C: User Acceptance Testing (UAT) can only begin one week after the backend system is fully developed because of a required data migration process.
(1) Describe a scenario where you would apply a lead to Task B concerning Task A and explain why.
(2) Describe how you would apply a lag between Task B and Task C and state the reasons for this decision.

## Slide 17: 2. Define Activities (cont’d)
A milestone is a significant event of the project
  Usually, don’t have a duration associated to it
  Several activities made a milestone
Milestones are good for setting
  Schedule goals
  Targets for team and as performance measures
  Reporting for upper management
Examples
  Customer sign-off on key documents
  Complete a feature

## Slide 18: 2. Define Activities (cont’d)
Milestones should always be SMART
  Specific
  Measurable
  Assignable
  Realistic
  Time-framed

## Slide 19: 3. Sequencing
Determine an order for all the activities to be undertaken
  Need to consider dependencies of activities
  Dependencies is needed to determine critical path
Types of dependencies
  Mandatory (inherent in the nature of work being performed)  No coding without design, no testing without coding
  Discretionary (also called soft logic)  Optional, no design without full system analysis
  External  Dependency to external (out of scope) activity. Involves relationship between project and non-project activities. E.g.: Installation of a software is dependent on a new hardware to be obtained form an external supplier.
(Project schedule) network diagrams or PERT chart

## Slide 20: Activity 3
You are the project manager for the construction of a new residential apartment building. This project includes various tasks such as obtaining permits, constructing the building foundation, framing, interior finishing, and arranging for utilities.
Before any construction can begin, you must obtain the necessary permits from the local government. Without these permits, it's illegal to start the construction.
The project plan suggests that interior finishing (like painting and installing fixtures) should start only after the building's framing is complete. However, there's flexibility in the schedule, and some tasks can start earlier if resources allow.
The local utility company is responsible for connecting the building to the electrical grid and water supply. This activity is dependent on the utility company's schedule and is outside the control of your project team.
Identify the type of dependencies and explain reasons.

## Slide 21: Task dependencies
Finish to Start: You cannot provide user training until after software has been installed.
Start to Start: A group of activities all start simultaneously.
Finish to Finish: Quality control efforts cannot finish before production finish
Start to Finish: An organization might strive to stock raw material just in time for the manufacturing process to begin. A delay in the manufacturing process starting should delay completion of stocking the raw material.
Notes: Start to start : related to concurrent engineering

## Slide 22: Activity 4
You are coordinating a software development project that includes two critical tasks: Task A involves writing the code for a new feature, and Task B involves creating the associated documentation that will be used by the end-users. You have decided that the documentation process should begin as soon as the coding starts because the documentation team can start outlining and preparing the basic structure and background sections while the developers are coding.
What is the relationship between A and B?
How is the scenario relevant to lead or lag?

## Slide 23: Showing Sequence
A network diagram is a display of activities and their sequences
Two methods
  Arrow (AOA)
  Precedence
diagramming (PDM)
AOA diagram

## Slide 24: Showing Sequence (cont’d)
PDM diagram

## Slide 25: Network Diagram points
Every activity on the network diagram must be completed in order for the project to finish.
Not every single item on the list need to be shown on the network diagram.
The precedence diagram method (PDM) is used more often than AOA as it provides various advantages.
  Only finish to start can be represented on AOA.
  We have to use dummy activities in AOA to show relationships.

## Slide 26: Precedence diagramming

## Slide 27: Precedence diagramming

## Slide 28: Precedence diagramming
Any type of dependencies, leads/lags can be presented through PDM

## Slide 29: 4. Determine duration -Resourcing (People / Equipment / Material)
You need to have
  Good idea of the quantity and
  Type of resources to be assigned to each activity
Consider the following
  How difficult will it be to complete specific activities on this project?
  What is the organization’s history in doing similar activities?
  Are the required resources available?
Output
  Resource Breakdown Structure: hierarchical structure that identifies the project’s resources by category and type.
  Resource categories may include: analyst, developers, testers, project managers.
Notes: fill in more information into the activity box
Resource estimation provides a basis ofr estimating activity duration. In addition, it is also releven to cost estimation (resource need cost), communication management and HR management.

## Slide 30: 4. Determine Duration
Duration includes
  Actual amount of time worked on an activity
  Elapsed time
Effort is the number of workdays or work hours required to complete a task
  Effort does not normally equal duration
People doing the work should help create estimates, and an expert should review them
Use 3-point estimate in PERT (program Evaluation and Review Technique): optimistic, most likely, pessimistic estimate.

## Slide 31: 5. Develop Schedule
Previous projects are good references!
  Determine the start and end dates of the project. Uses several iterations.
Always create a realistic schedule
  The first tool for monitoring progress
  Consequences of unrealistic schedule is BIG!
Many different tools
  Network diagram
  Gantt charts
  Critical path analysis
  Critical chain scheduling
  PERT analysis

## Slide 32: Gantt chart
Provides standard format of displaying project schedule information by listing project activities and their corresponding start and finish dates in calendar format
Activities on the Gantt Chart must coincide with the activity list and the milestone list
Gantt Chart contains milestones, summary tasks, individual task duration, and arrows showing task dependencies
You can create Milestones by creating a task (duration will be zero) and making it as milestone In MS Project

## Slide 33: Gantt chart (cont’d)

## Slide 34: Milestone/summary schedule in Gantt chart

## Slide 35: Detailed schedule in Gantt chart

## Slide 36: Activity 5
Draw a precedence diagram based on the following description on activities.
Activity A: "Market Research"
  Duration: 3 days
  Dependencies: None
Activity B: "Product Design"
  Duration: 5 days
  Dependencies: Starts after Activity A is completed
Activity C: "Prototype Creation"
  Duration: 4 days
  Dependencies: Can start 2 days before Activity B is completed (Lead: 2 days)
Activity D: "Product Testing"
  Duration: 6 days
  Dependencies: Cannot start until the Prototype Creation (Activity C) is completed
Activity E: "Marketing Plan Development"
  Duration: 4 days
  Dependencies: Starts 1 day after Market Research (Activity A) is completed (Lag: 1 day)
Activity F: "Production Planning"
  Duration: 3 days
  Dependencies: Can only start after both Product Design (Activity B) and Product Testing (Activity D) are completed

## Slide 37: Network diagram compared to Gannt
Network diagram is more technical, helps determine the critical path
Network diagram is not to a scaled timeline
Gantt is easy to read and explain to on-technical people
Gannt is a good method for graphically illustrating task progress and whether things are ahead of schedule or behind

## Slide 38: Preliminaries of critical path
Technique to predict total project duration
A critical path is series of activities that determines the earliest project completion time
  Is the longest path in a network diagram
  Has the least amount of slack or float
Slack (or float) is the amount of time an activity can be delayed without delaying
  a succeeding activity
  the project finish date

## Slide 39: Summary
Schedule management
  Plan
  Define activities
  Sequence activities
  Estimate duration
  Develop schedule
  Illustrate schedule (network diagram, Gantt chart)

## Slide 40: What’s next
More on techniques for project scheduling/monitoring/controlling - critical path analysis, PERT analysis