## Slide 1: SIT374/764: Project Management
Lecture 6: cost management

## Slide 2: Project management process groups
Initiation
Planning
Executing
Closing
Monitoring
Control
Approved Project Charter
Approved Project Management Plan
Customer signoff
Completion Report

## Slide 3: Project management process groups - Activity Map
Initiation
Planning
Executing
Mon. & Con.
Closing
Project Charter
Stakeholders
Register
Project Plan
Scope
Time
Cost
Quality
HR
Risk
Procurement
Stakeholders
Comm.
Project
Closing
Contract
Closing
Acquire & manage
team
Select Sellers &
POs
Perform QA
Comm.
Monitor &
Control Proj.
Cost control
Scope control &
verification
Schedule control
Progress Reporting
Manage Stakeholders
Contract Admin

## Slide 4: COST MANAGEMENT
IT projects have a poor record of meeting budget goals.
There is a scope for improvement in IT projects to meet the cost goals
We need to discuss
  Concepts of project cost management
  Estimating costs
  Determining the Budget
  Earned value management to control the costs

## Slide 5: COST MANAGEMENT
Cost overruns are caused by:
  original cost estimates being too low
  original cost estimates based on unclear project requirements
  many project managers think preparing cost estimates is a job for accountants
  untested technology
  untested business processes

## Slide 6: Cost vs. Revenue vs. Profit
Cost is resources expended to achieve a goal
  Usually measured in monetary units
  Cost management is the process to ensure project is completed within budget
Revenue is the income from the normal business activities
Profit (net benefit) = Revenue (benefit) – Cost (expenditure) (To increase profit : Reduce cost or Increase revenue)

## Slide 7: NPV analysis
NPV = discounted (benefit) – discounted (cost)
If… | It indicates… | Then…
NPV > 0 | the investment would add value to the firm | the project may be accepted
NPV < 0 | the investment would subtract value from the firm | the project should be rejected
NPV = 0 | the investment would neither gain nor lose value for the firm | indifferent in the decision This project adds no monetary value. Decision should be based on other criteria, e.g., strategic positioning or other factors not explicitly included in the calculation.

## Slide 8: Types of Costs
Fixed vs. variable cost:
  Fixed costs stay the costs that remain the same and do not change throughout the project life cycle . Examples of fixed costs include setup costs, rental costs etc.
  Variable costs are costs that change with the amount of work. Examples of variable costs are hourly labor, cost of material, cost of supply, fuel etc.
Tangible vs. Intangible cost
  Tangible costs or benefits are those costs or benefits that an organization can easily measure in dollars
    A task that was allocated $150,000 but actually costs $100,000 would have a tangible benefit of $50,000 if the assets allocated are used for other projects
  Intangible costs or benefits are costs or benefits that are difficult to measure in monetary terms
    Costs – resources used to research related areas of a project but not billed to the project
    Benefits – goodwill, prestige, general statements of improved productivity not easily translated in dollars

## Slide 9: TYPEs of Costs
Direct costs are costs that can be directly related to producing the products and services of the project
  Salaries, cost of hardware and software purchased specifically for the project
Indirect costs are costs that are not directly related to the products or services of the project, but are indirectly related to performing the project
  Cost of electricity, paper towels
Sunk cost is money that has been spent in the past; when deciding what projects to invest in or continue, you should not include sunk costs
  To continue funding a failed project because a great deal of money has already been spent on it is not a valid way to decide on which projects to fund
  Sunk costs should be forgotten

## Slide 10: TYPEs of Costs
Reserves are dollars included in a cost estimate to mitigate cost risk by allowing for future situations that are difficult to predict
  Contingency reserves allow for future situations that may be partially planned for (sometimes called known unknowns) and are included in the project cost baseline
    Recruiting and training costs for expected personnel turnover during a project
  Management reserves allow for future situations that are unpredictable (sometimes called unknown unknowns)
    Extended absence of a manager; supplier goes out of business

## Slide 11: Activity 1
Based on the information provided in Cost management-Activity 1, identify the types of costs associated with this IT project. Categorize each cost.

## Slide 12: Processes in Cost Management
Determine Project Budget
Control Cost
Estimate Activity Cost
Plan Cost Management
Planning
Monitoring and
Controlling

## Slide 13: 1. Plan cost management
Plan cost management is the process of defining how the costs will be estimated, budgeted, monitored, and controlled.
Key inputs include the project charter, schedule management plan, and organizational process assets.
The main output is the schedule management plan.
Sample Cost Management Plan

## Slide 14: cost management plan
Cost management plan is a component of project management plan and describes how the cost will be planned, structured, and controlled. Can establish the following:
  Tools/techniques used
  Units of measure
  Level of precision
  Control thresholds
  Rules of performance measurement
    Earned value management (EVM)
  Reporting format

## Slide 15: 2. estimate costs
Estimate Costs is the process of developing an approximation or estimate of the costs of the resources needed to complete a project.
  Key benefit is that it determines the monetary resources required for the project.
Cost estimates

## Slide 16: TYPES OF ESTIMATES
Rough order magnitude (ROM) : Ballpark estimate. Done very early in the project (even before the project starts). Accuracy : -50 to +100% (actual cost could be 50% below or 100% above this estimate)
A Budgetary Estimate: Made 1-2 years prior to the project completion. Used to allocate money to the organization’s budget. Accuracy : -10% to +25%
Definitive Estimate: Provides accurate estimates of the project cost and is used to make purchasing decisions.

## Slide 17: Estimation techniques
Analogous Estimate: similar project is the basis for estimating the cost. Less costly, but less accurate.
Bottom-Up Estimate: involves estimating individual work items or activities to get the project total cost. Also called activity-based costing.
  Accuracy of the estimate depends upon: size of the individual work item and experience of the estimator.
Parametric modelling: uses project characteristics (parameters) in a mathematical model to estimate project cost. Reliable when historical information is available.
  Software application -COCOMOII model (uses size of the software) and characteristics of software.

## Slide 18: Activity 2
Based on the information provided in Cost management-Activity 2, calculate the estimated software development cost for the project.

## Slide 19: WBS and activity-level estimate
Cost estimation at WBS level
  Used in early stages when detailed task-level information may not be fully developed.
  Useful for initial budgeting and securing funding.
Cost estimation in activity level
  Used once the activities are detailed out.
  Provides more detailed and accurate cost estimate.

## Slide 20: Cost estimate
For various WBS items/activities we need cost per unit and total number in units.
Contingency reserves are calculated : Usually, 20% of total project cost estimate
  Useful to estimate the total cost for each category (especially for higher management)

## Slide 21: SAMPLE Cost Estimate
Notes: Surveyor Pro Project : Cost estimate for Internet Site project (Kathy Schwalbe)
Contingency Reserves : 1,267,700 * (20/100)

## Slide 22: 3. Determine budget
Determine Budget is the process of aggregating the estimated costs to create project budget and an authorized cost baseline.
  Key benefit is that it determines the cost baseline which project performance can be monitored and controlled.
Project budget, cost baseline, funding requirements
Notes: The ultimate
goal of developing the schedule is to create a realistic project schedule that provides
a basis for monitoring project progress for the time dimension of the project.
The schedule development is the final deliverable of time management in terms of planning. All the previous docs like activity, dependency, resource are acting as the input for making the schedule.

## Slide 23: Budget and Cost Baseline
Cost baseline: approved version of time-framed project budget, excluding management reserves.
  Cost estimates make up the cost baseline
  Since cost baseline is tied to schedule activities, it has a time-phased view.
Budget: produced by adding management reserves to cost baseline
  Change control process can be used to move management reserve into cost baseline

## Slide 24: Sample Cost Baseline
*Numbers are rounded, so some totals appear to be off.

## Slide 25: Budget component

## Slide 26: Funding requirements
Derived from cost baseline
Total funds are those
included in cost baseline
plus management reserves
Often occurs in
incremental amounts

## Slide 27: 4. Cost Control
Monitoring expenditure
  Gain insights into performance information
Controlling changes to the project budget

## Slide 28: Earned Value Management (EVM)
EVM: Project performance management technique involves all the three project constraints (scope, time, cost).
  Integrates scope baseline with cost baseline, and schedule baseline to form performance measurement baseline.
  Given a project baseline, EVM allows to measure how well project meets goals. (By entering actual information and then comparing it to the baseline)

## Slide 29: Three key dimensions to be monitored
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS): portion of total cost estimate planned to be spent on an activity in a given period.
Actual Cost (AC) or Actual Cost of Work Performed (ACWP): is direct and indirect cost incurred on an activity during a given period.
  Earned Value (EV) or Budgeted Cost of Work Performed (BCWP): is estimate of physical work actually completed.
    (EV is based on the original planned costs for the project or activity and the rate at which the team is completing work on the project or activity to date)
Notes: Rate of Performance (RP) : E.g. : server installation was completed halfway by the end of Week 1. The rate of performance would be 50% (50/100), bacasue by the end of the week only 50% of the work could be completed.

## Slide 30: Variance analysis
Determine the degree of variance between the baseline and the actual project performance.
Schedule variance (SV): the amount the project is ahead or behind the planned delivery date. SV=EV-PV
Cost variance (CV): the amount of project deficit or surplus at a given point. CV=EV-AC
Schedule performance index (SPI): schedule efficiency. SPI=EV/PV
Cost performance index (CPI): cost efficiency. CPI=EV/AC

## Slide 31: Variance Calculations for One Activity After Week One

## Slide 32: Variance insights
Negative numbers for cost and schedule variance indicate problems in those areas
A CPI or SPI that is less than 100% indicates problems means the project is
  costing more than planned (over budget)
  taking longer than planned (behind schedule)

## Slide 33: Trend analysis
Determine the performance over time to determine if the performance is improving or not.
Forecast future performance.
Budget at completion (BAC): the original total budget for the project.
Estimate at completion (EAC): a forecast/estimate of what it will cost to complete the project

## Slide 34: Estimate at completion (EAC)
A few methods could be used to compute EAC. 2 most commonly used are:
EAC based on the budgeted rate: accepts the actual costs, and predict all future work will be accomplished at the budgeted rate. EAC=AC+BAC-EV
EAC based on the present CPI: assumes that what the project experienced to date can continue in the future. EAC=BAC/CPI
EAC based on both CPI and SPI: effective when schedule is an impacting factor. EAC=AC+(BAC-EV)/(CPISPI)

## Slide 35: Estimated time to completion
Estimated time to completion is based on actual elapsed time and forecasted remaining time.
Original Project Duration (OPD): initially planned duration of the project
Elapsed Time (ET): time that has already been spent
Estimated Time to Completion (ETC): ETC=ET+(OPD-ET)/SPI
Other methods to compute ETC? How to select?

## Slide 36: Earned Value Chart

## Slide 37: Earned Value Chart
The chart helps visualize how the project is performing.
  If the project goes as planned, it will finish in 12 months at a cost of $100,000
  The actual cost line is always right on or above the earned value line.
    Interpretation: This means costs are equal to or more than planned
  The planned value line is pretty close to the EV line, just slightly higher in the last month
    Interpretation: The project has been right on schedule until last month when the project fell behind schedule

## Slide 38: EVM Example

## Slide 39: Activity 3
Based on the information provided in Cost management-Activity 3,
Calculate the Cost Variance (CV) and Schedule Variance (SV) at the end of the sixth month.
Determine the Cost Performance Index (CPI) and Schedule Performance Index (SPI) at this point in the project.
Given the discovered underestimation, calculate the Estimate at Completion (EAC) assuming the current cost performance will continue for the remainder of the project.
Compute the Estimated Completion Time (ECT), assuming the current rate of progress continues, and compare it with the original schedule.
Discuss the implications of these findings and recommend strategies for the project manager to address the project's current status.

## Slide 40: Summary
Cost management
  Plan
  Estimate cost
  Determine budget
  Cost control
    EVM, variance analysis, trend analysis
    SV, CV, CPI, SPI, EAC, BAC, ETC

## Slide 41: What’s next
Next area of project management – risk management